## FRC 2012-2013
Task List - FIRST Robotics
|  | Updated by: | [5 empty] | Completed tasks | 0 of 151
Revision date:
Phase |  | Tasks | Resp. | Pre-saison | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.Planning |  | - Team -
.Planning | 1 | Contact and integration of mentors/coordinators to the team | [9 empty] | 0
.Planning | 2 | Division of labour: by sub-groups, project managers or other means | [9 empty] | 0
.Planning | 3 | Identification of mentors for sub-groups or project managers | [9 empty] | 0
.Planning | 4 | Training sessions for mentors | [9 empty] | 0
.Planning | 5 | Training sessions for students: safety, tool usage, metal work techniques | [9 empty] | 0
.Planning | 6 | CSDM: CSST work shop training | [9 empty] | 0
.Planning |  | - Logistics -
.Planning | 7 | Access (keys) to the school, class, lab | [9 empty] | 0
.Planning | 8 | Calendar of meetings made available | [9 empty] | 0
.Planning | 9 | Registration with online suppliers | [9 empty] | 0
.Planning | 10 | Installation of software: CAD, LabVIEW 2012, etc. | [9 empty] | 0
.Planning | 11 | Parental consent (for students) and background checks (for external adults) completed | [9 empty] | 0
.Planning | 12 | Registration/update of information in TIMS/STIMS before December 20 2012 | [9 empty] | 0
.Planning |  | - Project -
.Planning | 13 | Communication/marketing plan operational | [9 empty] | 0
.Planning | 14 | Business plan operational | [9 empty] | 0
.Planning |  | - Resources -
.Planning | 15 | Inventory of tools and materials | [9 empty] | 0
.Planning | 16 | Availability of hardware and required materials | [9 empty] | 0
.Planning | 17 | Availability of all required tools | [9 empty] | 0
.Planning | 18 | Availability of pool noodles for bumpers | [9 empty] | 0
.Planning | 19 | Availability of bumper fabric | [9 empty] | 0
.Planning | 20 | Access to game manual (rules) of FRC-2013 game - January 5 2013 | [9 empty] | 0
.Planning | 21 | Access to/download of LabVIEW and updates/utilities - January 5 2013 | [9 empty] | 0
.Planning | 22 | Reception of KoP - January 5 2013 | [9 empty] | 0
.Planning | 23 | Availability of work gloves and safety glasses in sufficient quantities | [9 empty] | 0
.Planning | 24 | Availability of laptops for the project: drivers' station, programming, CAD, etc. | [9 empty] | 0
Design |  | - Team -
Design | 1 | Division of labour and responsibilities | [9 empty] | 0
Design | 2 | Supervision and guidance of sub-groups by adults | [9 empty] | 0
Design | 3 | Communication and decision making process clear | [9 empty] | 0
Design | 4 | Debriefing: evaluation of progress, risk and problem identification | [9 empty] | 0
Design |  | - Logistics -
Design | 5 | Installation and update of software: LabVIEW etc. | [9 empty] | 0
Design | 6 | Reading and communication of team updates - game and administrative manuals | [9 empty] | 0
Design | 7 | BoM update - house version | [9 empty] | 0
Design | 8 | Budget update | [9 empty] | 0
Design |  | - Project -
Design | 9 | Game manual (rules) for FRC-2013 game read and understood | [9 empty] | 0
Design | 10 | Brainstorming/decision making - Game strategy for each period of play | [9 empty] | 0
Design | 11 | Brainstorming/decision making - Drive base: chassis, drive train, gearing, wheels | [9 empty] | 0
Design | 12 | Brainstorming/decision making - Mechanisms | [9 empty] | 0
Design | 13 | Design - Chassis and drive train | [9 empty] | 0
Design | 14 | Design - Bumpers | [9 empty] | 0
Design | 15 | Design - Mechanisms | [9 empty] | 0
Design | 16 | List of motors, controllers and sensors required | [9 empty] | 0
Design | 17 | Design - Electronics board | [9 empty] | 0
Design | 18 | Design - Pneumatics system | [9 empty] | 0
Design | 19 | Prototyping of mechanisms | [9 empty] | 0
Design | 20 | Programming - cRIO imaged | [9 empty] | 0
Design | 21 | Programming - Router configured | [9 empty] | 0
Design | 22 | Programming - Basic architecture, motors | [9 empty] | 0
Design | 23 | Design - Pit | [9 empty] | 0
Design | 24 | Design - Robot cart | [9 empty] | 0
Design | 25 | Design - shipping crate | [9 empty] | 0
Design |  | - Spot checks -
Design | 26 | Dimensions/weight of robot comply with rules | [9 empty] | 0
Design | 27 | Bumpers comply with rules | [9 empty] | 0
Design | 28 | Materials comply with rules | [9 empty] | 0
Design |  | - Resources -
Design | 29 | E-mail blasts/updates - Game manual (rules) of FRC-2013 game | [9 empty] | 0
Design | 30 | Order of materials from suppliers starting January 7 2013 | [9 empty] | 0
Design | 31 | KoP inventory | [9 empty] | 0
Design | 32 | Order of missing KoP pieces (through TIMS) January 7-11 2013 | [9 empty] | 0
Design | 33 | FIRST-Choice order starting Dec. 10th 2012 or Jan. 7th 2013 | [9 empty] | 0
Execution |  | - Team -
Execution | 1 | Division of labour and responsibilities | [9 empty] | 0
Execution | 2 | Supervision and guidance of sub-groups by adults | [9 empty] | 0
Execution | 3 | Debriefing: evaluation of progress, risk and problem identification | [9 empty] | 0
Execution |  | - Logistics -
Execution | 4 | Reading and communication of team updates - game and administrative manuals | [9 empty] | 0
Execution | 5 | BoM update - house versionn | [9 empty] | 0
Execution | 6 | Budget update | [9 empty] | 0
Execution |  | - Project - | [9 empty] | 0
Execution | 7 | Construction - Drive base | [9 empty] | 0
Execution | 8 | Construction - Bumpers | [9 empty] | 0
Execution | 9 | Prototyping of mechanisms | [9 empty] | 0
Execution | 10 | Construction - Mechanisms - regular gameplay | [9 empty] | 0
Execution | 11 | Construction - Mechanisms - end game, if necessary | [9 empty] | 0
Execution | 12 | Construction - Electronics board | [9 empty] | 0
Execution | 13 | Construction - Power circuit | [9 empty] | 0
Execution | 14 | Construction - Signal circuit | [9 empty] | 0
Execution | 15 | Construction - Power circuits for mechanisms (motors, compressor) | [9 empty] | 0
Execution | 16 | Construction - Sensor circuits | [9 empty] | 0
Execution | 17 | Construction - Pneumatics system | [9 empty] | 0
Execution | 18 | Construction - Integration of modules/mechanisms to drive base | [9 empty] | 0
Execution | 19 | Construction - Integration of electronics board to drive base | [9 empty] | 0
Execution | 20 | Programming - Drive motors | [9 empty] | 0
Execution | 21 | Programming - Mechanisms and sensors | [9 empty] | 0
Execution | 22 | Programming - Autonomous mode | [9 empty] | 0
Execution | 23 | Programming - End game, if necessary | [9 empty] | 0
Execution | 24 | Construction - Pit | [9 empty] | 0
Execution | 25 | Construction - Robot cart | [9 empty] | 0
Execution | 26 | Construction - Shipping crate | [9 empty] | 0
Execution | 27 | Construction - Field/field elements/game pieces for driver practice | [9 empty] | 0
Execution |  | - Spot checks - | [9 empty] | 0
Execution | 28 | Test 1 Communication with drive base (wired and wireless) : successful | [9 empty] | 0
Execution | 29 | Test 2 Locomotion of drive base (control of movements) : successful | [9 empty] | 0
Execution | 30 | Test 3 Locomotion of drive base (speed control) : successful | [9 empty] | 0
Execution | 31 | Test 4 Mechanisms for regular gameplay: successful | [9 empty] | 0
Execution | 32 | Test 5 Pneumatics system (function and integrity): successful | [9 empty] | 0
Execution | 33 | Test 6 Basic end game (functions specific to end game) : successful | [9 empty] | 0
Execution | 34 | Test 7 Basic autonomous: successful | [9 empty] | 0
Execution | 35 | Dimensions/weight of robot comply with rules | [9 empty] | 0
Execution | 36 | Bumpers comply with rules | [9 empty] | 0
Execution | 37 | Materials comply with rules | [9 empty] | 0
Execution | 38 | Extension of mechanisms complies with rules | [9 empty] | 0
Execution | 39 | Quantity/type of motors complies with rules | [9 empty] | 0
Execution | 40 | Use and connection of motor controllers and relays complies with rules | [9 empty] | 0
Execution | 41 | Power/control of motors and actuators complies with rules | [9 empty] | 0
Execution | 42 | Energy storage (electric, pneumatic, mechanical) complies with rules | [9 empty] | 0
Execution | 43 | Accessibility of electronics panel/main breaker/signal light complies with rules | [9 empty] | 0
Execution | 44 | Use of fuses and breakers complies with rules | [9 empty] | 0
Execution | 45 | Power supply to router/radio complies with rules | [9 empty] | 0
Execution | 46 | Robot wiring (gauge and colour) complies with rules | [9 empty] | 0
Execution | 47 | Electric circuits comply with rules | [9 empty] | 0
Execution | 48 | Pneumatics system complies with rules | [9 empty] | 0
Execution | 49 | Connection and power to solenoids comply with rules | [9 empty] | 0
Execution | 50 | Use of pneumatic security systems (relief valves, pressure switch, regulator) complies with rules | [9 empty] | 0
Execution | 51 | Use of wired/wireless communication complies with rules | [9 empty] | 0
Execution | 52 | Emergency-stop button wired according to rules | [9 empty] | 0
Execution | 53 | Use/connection/charging of batteries comply with rules | [9 empty] | 0
Execution | 54 | No risk of robot harming people (no sharp corners, no exposed chains etc.) | [9 empty] | 0
Execution | 55 | No risk of robot damaging other robots or playing field | [9 empty] | 0
Execution | 56 | Decorative elements on robot comply with rules | [9 empty] | 0
Execution | 57 | Identification of team/team number/sponsors on robot according to rules | [9 empty] | 0
Execution |  | - Resources -
Execution | 58 | E-mail blasts/updates - Game manual (rules) of FRC-2013 game | [9 empty] | 0
Execution | 59 | Order of materials from suppliers | [9 empty] | 0
Optimization |  | - Team -
Optimization | 1 | Division of labour and responsibilities | [9 empty] | 0
Optimization | 2 | Supervision and guidance of sub-groups by adults | [9 empty] | 0
Optimization | 3 | Choice of drive team and definition of roles and responsibilities | [9 empty] | 0
Optimization | 4 | Definition of roles and responsibilities for other team members during competition | [9 empty] | 0
Optimization | 5 | Driver practice sessions | [9 empty] | 0
Optimization | 6 | Debriefing: evaluation of progress, risk and problem identification | [9 empty] | 0
Optimization |  | - Logistics -
Optimization | 7 | Creation of checklists/maintenance routine | [9 empty] | 0
Optimization | 8 | List of spare parts/tools/materials to bring to competition | [9 empty] | 0
Optimization | 9 | Reading and communication of team updates - game and administrative manuals | [9 empty] | 0
Optimization | 10 | BoM update - house version | [9 empty] | 0
Optimization | 11 | Budget update | [9 empty] | 0
Optimization |  | - Project -
Optimization | 12 | Construction - Driver station according to rules | [9 empty] | 0
Optimization | 13 | Pit disassembly | [9 empty] | 0
Optimization | 14 | Optimization of robot code | [9 empty] | 0
Optimization | 15 | Bumpers attach/detach easily | [9 empty] | 0
Optimization |  | - Spot checks -
Optimization | 16 | Robustness of systems | [9 empty] | 0
Optimization | 17 | Modularity of systems | [9 empty] | 0
Optimization | 18 | Transition between modes of gameplay | [9 empty] | 0
Optimization | 19 | Test 8 Precision of mechanisms: successful | [9 empty] | 0
Optimization | 20 | Test 9 FIRST FRC Robot checklist : successful | [9 empty] | 0
Optimization | 21 | Test 10 FIRST safety rules - robot/pits (safety manual) : successful | [9 empty] | 0
Optimization | 22 | Test 11 Robot in gameplay situations (if possible): successful | [9 empty] | 0
Wrap-Up |  | - Team -
Wrap-Up | 1 | Division of labour and responsibilities | [9 empty] | 0
Wrap-Up | 2 | Supervision and guidance of sub-groups by adults | [9 empty] | 0
Wrap-Up | 3 | Debriefing: evaluation of progress, risk and problem identification | [9 empty] | 0
Wrap-Up | 4 | Debriefing: marketing/finance/awards strategy | [9 empty] | 0
Wrap-Up |  | - Logistics -
Wrap-Up | 5 | Reading and communication of team updates - game and administrative manuals | [9 empty] | 0
Wrap-Up | 6 | Budget update | [9 empty] | 0
Wrap-Up | 7 | BoM update - Official FIRST version (on USB key) | [9 empty] | 0
Wrap-Up |  | - Project -
Wrap-Up | 8 | Pit disassembled, ready for transport | [9 empty] | 0
Wrap-Up | 9 | Weighing of pieces to remain outside bag, according to rules | [9 empty] | 0
Wrap-Up | 10 | Tools, materials and spare parts ready for transport | [9 empty] | 0
Wrap-Up | 11 | Robot bagged and tagged according to rules | [9 empty] | 0
Wrap-Up | 12 | Robot lockup form completed (to be presented at competition) | [9 empty] | 0
Wrap-Up | 13 | Photo of sealed robot sent to FIRST Quebec | [9 empty] | 0